## provide it in the sheet s
REF ID | RISK | RISK OWNER | RISK TRIGGER | RISK CATEGORY | Probability | Impact | Severity | Expected Result
R1 | Insufficient budget allocation | Project Manager | Reduced funding, increased costs | Financial | 2 (Moderate) | 3 (High) | 6 | Delayed project activities, reduced scope
R2 | Inadequate target audience research | Marketing Manager | Incorrect audience identification, ineffective messaging | Market Research | 2 (Moderate) | 3 (High) | 6 | Reduced campaign effectiveness, low engagement
R3 | Negative social media comments | Social Media Manager | Critical comments, online disputes | Reputation | 3 (High) | 2 (Moderate) | 6 | Damaged brand reputation, decreased trust
R4 | Resource constraints (personnel, equipment) | Project Manager | Lack of available staff, inadequate tools | Operational | 2 (Moderate) | 2 (Moderate) | 4 | Project delays, reduced productivity
R5 | Technical issues (platform, software) | IT Department | System failures, data loss, security breaches | Technical | 2 (Moderate) | 3 (High) | 6 | Campaign disruption, data loss