## Sheet1
Task | Priority | Owner | Status | Start date | End date | Milestone | Deliverable | Notes
Project Charter | P1 | maheswar barrenkala | Completed | 2024-07-16 | 2024-07-18
WBS | P2 | maheswar barrenkala | Completed | 2024-07-26 | 2024-07-26
Tak Estimation | P2 | maheswar barrenkala | Completed | 2024-07-30 | 2024-07-31
Budget Plan | P2 | maheswar barrenkala | Completed | 2024-07-31 | 2024-07-31
Gantt Chart | P1 | amanda.liu7613@gmail.com | Completed | 2024-07-26
Communication Plan | P2 | maheswar barrenkala | Completed | 2024-07-31 | 2024-07-31
Quality plan / test plan | P1 | maheswar barrenkala | Completed | 2024-08-10 | 2024-08-10
RESPONSIBILITY ASSIGNMENT MATRIX | P2 | amanda.liu7613@gmail.com | Completed | 2024-08-08 | 2024-08-10
Risk Register | P2 | maheswar barrenkala | Completed | 2024-08-09 | 2024-08-10