## Gantt Chart
Gantt Chart: Team 1
PROJECT TITLE |  | Social Media Marketing Campaign for Naz University |  |  |  |  | COMPANY NAME | Team 1
PROJECT MANAGER |  | Maheswar |  |  |  |  | DATE
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE |  | PHASE TWO |  |  |  | PHASE THREE |  | PHASE FOUR | PHASE FIVE | PHASE EIGHT
[7 empty] | WEEK 1 | WEEK 2 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | MONTH 18
1 | Project Planning and Pre-Development |  | 2024-07-01 | 2024-07-12 | 12
1.1 | Define project goals |  | 2024-07-01 | 2024-07-04 | 3 | 100% | bar: WEEK 1
1.2 | Establish project team |  | 2024-07-05 | 2024-07-08 | 3 | 100% | bar: WEEK 1
1.3 | Stakeholder meetings |  | 2024-07-09 | 2024-07-11 | 2 | 100% | bar: WEEK 1 to WEEK 2
1.4 | Market Research and Strategy Development |  | 2024-07-12 | 2024-07-16 | 4 | 100% | bar: WEEK 2
2 | Implementation |  | 2024-07-13 | 2024-08-05 | 22
2.1 | Video Production |  | 2024-07-13 | 2024-07-18 | 5 | 100% | bar: WEEK 2 to WEEK 3
2.2 | Image Design |  | 2024-07-19 | 2024-07-21 | 2 | 100% | bar: WEEK 3
2.3 | Website and submission platform |  | 2024-07-22 | 2024-07-27 | 5 | 100% | bar: WEEK 4
2.4 | Public relations campaign |  | 2024-07-28 | 2024-07-31 | 3 | 100% | bar: WEEK 5
2.5 | Community engagement activities |  | 2024-08-01 | 2024-08-05 | 4 | 100% | bar: WEEK 5
3 | Monitoring, Control, and Closing |  | 2024-08-06 | 2024-08-19 | 13
3.1 | Performance Measurement and Reporting |  | 2024-08-06 | 2024-08-09 | 3 | 100% | bar: WEEK 5
3.2 | Risk Monitoring and Management |  | 2024-08-10 | 2024-08-12 | 2 | 100% | bar: WEEK 5
3.3 | Change Control |  | 2024-08-13 | 2024-08-15 | 2 | 100% | bar: WEEK 5 to WEEK 6
3.4 | Quality Assurance |  | 2024-08-16 | 2024-08-17 | 1 | 100% | bar: WEEK 6
3.5 | Stakeholder Management |  | 2024-08-18 | 2024-08-19 | 1 | 100% | bar: WEEK 6
4 | Closing |  | 2024-08-20 | 2024-08-24 | 4
4.1 | Project Evaluation and Documentation |  | 2024-08-20 | 2024-08-21 | 1 | 100% | bar: WEEK 7
4.2 | Knowledge Transfer |  | 2024-08-22 | 2024-08-23 | 1 | 100% | bar: WEEK 7
4.3 | Final Report and Presentation |  | 2024-08-24 | 2024-08-24 | 0 | 100% | bar: WEEK 7
4.4 | Project Closure |  | 2024-08-24 | 2024-08-25 | 1 | 100% | bar: WEEK 7
5 | Post-Implementation |  | 2024-08-25 | 2024-09-01 | 6
5.1 | Performance monitoring |  | 2024-08-25 | 2024-08-27 | 2 | 0% | bar: WEEK 8
5.2 | Maintenance |  | 2024-08-27 | 2024-08-28 | 1 | 0% | bar: WEEK 8
5.3 | Continuous improvement |  | 2024-08-28 | 2024-08-29 | 1 | 0% | bar: WEEK 8
5.4 | Impact evaluation |  | 2024-08-30 | 2024-08-31 | 0 | 0% | bar: WEEK 8
8 | Closeout |  | 2024-09-01 | 2025-06-30 | 299
8.1 | Project closure documentation |  | 2024-09-01 | 2024-09-07 | 6 | 0% | bar: MONTH 18
8.2 | Finalize project report |  | 2024-09-08 | 2024-09-15 | 7 | 0% | bar: MONTH 18
8.3 | Stakeholder communication |  | 2024-09-16 | 2024-09-23 | 7 | 0% | bar: MONTH 18
8.4 | Release project resources |  | 2024-09-24 | 2024-09-30 | 6 | 0% | bar: MONTH 18
Formulas:
START DATE = [START DATE, row above]
START DATE = [DUE DATE, row above]+1
DUE DATE = [START DATE]+3